Project Plan

LMNL.app

| Industry Partner | N/A |
| --- | --- |
| Primary Instructor | Laily Ajellu |
| Team Member | Samin Qureshi |
| Team Member | Soman Ahmad |
| Team Member | Pierre-Anthony Eid |
| Team Member | Talalovic Ababakar |

Document Revision History

| Revision # | Date |
| --- | --- |
| 1.0 | Oct 25, 2025 |

Contents

1. Executive Summary	3

2. Project Approvers, Reviews and Distribution List	3

3. Scope	4

4. Deliverables	4

5. Assumptions	5

6. Dependencies	5

8. Communication	6

Reporting	6

Meetings	6

9. Task Listing (WBS- Work Breakdown Structure)	6

10. Gantt Chart	7

Legend:	8

Notes:	8

11. Milestones	8

12. RAM – Responsibility Assignment Matrix	8

RACI Model	8

RACI Legend:	9

Notes:	9

13. Approval	9

# 1. Executive Summary

The following describes the project to be executed.

| Objective | Develop a cross-platform social media application (Android and iOS) that prioritizes quality over quantity by enforcing daily limits on posts, likes, and comments, promoting digital wellbeing and meaningful interactions. |
| --- | --- |
| Corporate Goals Addressed | - Promote digital wellbeing and intentional social media use - Deliver a fully functional mobile application with local hosting capabilities - Demonstrate technical proficiency in cross-platform mobile development - Create comprehensive documentation for future development |
| Planned Start Date | September 16, 2025 |
| Planned End Date | March 28, 2026 |

# 2. Project Approvers, Reviews and Distribution List

Approvers, reviewers and distribution list

| Project Role | Name | E-mail | Date |
| --- | --- | --- | --- |
| Instructor | Laily Ajellu | laily.ajellu@georgebrown.ca | Oct 26, 2025 |
| Back-End Engineer | Soman Ahmad | soman.ahmad@georgebrown.ca | Oct 26, 2025 |
| Database Engineer | Samin Qureshi | samin.qureshi@georgebrown.ca | Oct 26, 2025 |
| Front-End Engineer | Pierre-Anthony Eid | pierre-anthony.eid@georgebrown.ca | Oct 26, 2025 |
| UI/UX Designer | Talalovic Ababakar | talalovic.ababakar@georgebrown.ca | Oct 26, 2025 |

# 3. Scope

Define the sum total of all of its products and their requirements or features.

| In Scope | Out of Scope |
| --- | --- |
| Code development for Android and iOS platforms | Cloud hosting services |
| Comprehensive technical and user documentation | Domain name purchase and registration |
| User interface and experience testing | External server configuration |
| Feature testing and debugging | App Store and Google Play Store publishing |
| Local server and database hosting | Post-project maintenance and updates |
| User authentication and authorization system | Payment gateway integration |
| Post creation, viewing, and interaction features | Video content support |
| Daily limit enforcement system | Advanced analytics and reporting |

# 4. Deliverables

This project will deliver the following.

| Deliverable | Description |
| --- | --- |
| Mobile Application | Functional iOS and Android app with complete feature set, locally hosted with potential for public app store release. |
| Authentication System | Full-fledged user authentication and authorization system with secure login capabilities. |
| Limited Interaction Features | User capability to view posts, create posts, and interact within defined limits: 10 posts per feed per day, 5 likes, and 5 comments. |
| Local Database | Locally integrated database capable of storing and fetching data in an optimized fashion based on API interactions. |
| Documentation | Comprehensive technical documentation including codebase documentation, user guides, and system architecture documents. |

# 5. Assumptions

This project makes the following assumptions:

- Users will prefer meaningful, intentional interactions over addictive scrolling.

- A limited feed model will encourage higher content quality.

- Platform can differentiate itself by emphasizing quality over quantity and digital wellbeing.

- Target audience (students and professionals) values time management and digital wellbeing.

- Local hosting will be sufficient for initial project scope and testing.

- Team members have the necessary technical skills or ability to learn required technologies.

- Development tools and environments will remain available throughout the project timeline.

# 6. Dependencies

The following are the internal and external dependencies that will have to be acknowledged and addressed:

- Availability of development environments and tools (IDEs, simulators, testing devices)

- Access to required software licenses and frameworks

- Team member availability and time commitment

- Instructor and stakeholder feedback on deliverables

- Stable internet connectivity for collaboration and research

- Third-party libraries and frameworks for authentication and database management

7. Risk Management

| Potential Risk | Severity (H/M/L) | Likelihood (H/M/L) | Management Strategy |
| --- | --- | --- | --- |
| Technical skill gaps | H | M | Allocate time for learning, pair programming, and knowledge sharing sessions |
| Scope creep | M | M | Strict adherence to documented scope, regular review meetings |
| Team member unavailability | H | L | Cross-training team members, maintaining detailed documentation |
| Integration issues | M | M | Early and continuous integration testing, modular architecture |
| Timeline delays | M | M | Build buffer time into schedule, prioritize critical features |

# 8. Communication

## Reporting

The following reports will be produced;

| Report | Audience | Frequency |
| --- | --- | --- |
| Project Status Report | Instructor, Team Members | Weekly |
| Sprint Review | Instructor, Team Members | Bi-weekly |
| Final Project Report | Instructor, Stakeholders | End of Project |

## Meetings

The following meetings/communication will be established;

| Meeting | Purpose | Attendees | Frequency |
| --- | --- | --- | --- |
| Team Stand-up | Daily progress updates and blockers | All Team Members | Daily (via Discord) |
| Sprint Planning | Plan sprint activities and assign tasks | All Team Members | Bi-weekly |
| Instructor Review | Present progress and receive feedback | Team Members, Instructor | Weekly |

# 9. Task Listing (WBS- Work Breakdown Structure)

The following resource proposal template summarizes the resource hours committed to this project, upon final approval of this document.

| Reference | Tasks | Duration | Dependency |
| --- | --- | --- | --- |
| A | Project Planning and Requirements Analysis | 2 weeks | None |
| B | UI/UX Design and Wireframing | 3 weeks | A |
| C | Database Design and Implementation | 4 weeks | A |
| D | Back-End Development (API, Authentication) | 6 weeks | C |
| E | Front-End Development (iOS/Android) | 8 weeks | B, D |
| F | Integration and System Testing | 4 weeks | E |
| G | User Acceptance Testing and Bug Fixes | 2 weeks | F |
| H | Documentation and Final Deliverables | 2 weeks | G |

# 10. Gantt Chart

September 2025 - March 2026

| Task | Sept-Oct 2025 |  | Nov-Dec 2025 |  | Jan-Feb 2026 |  | Mar 2026 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Duration | W1-4 | W5-8 | W9-12 | W13-16 | W17-20 | W21-24 | W25-26 | W27-28 |
| A. Project Planning & Requirements (2 weeks) | █████ |  |  |  |  |  |  |  |
| B. UI/UX Design & Wireframing (3 weeks) |  | █████ |  |  |  |  |  |  |
| C. Database Design & Implementation (4 weeks) |  | ████ | █ |  |  |  |  |  |
| D. Back-End Development (6 weeks) |  |  | ████ | █████ | █ |  |  |  |
| E. Front-End Development (8 weeks) |  |  |  | ████ | █████ | █████ | ██ |  |
| F. Integration & System Testing (4 weeks) |  |  |  |  |  | ████ | █████ |  |
| G. UAT & Bug Fixes (2 weeks) |  |  |  |  |  |  | ███ | ██ |
| H. Documentation & Final Deliverables (2 weeks) |  |  |  |  |  |  |  | █████ |

## Legend:

■ Project Planning & Requirements    ■ UI/UX Design & Wireframing

■ Database Design & Implementation    ■ Back-End Development

■ Front-End Development    ■ Integration & System Testing

■ UAT & Bug Fixes    ■ Documentation & Final Deliverables

## Notes:

• Total project duration: 28 weeks (September 16, 2025 - March 28, 2026)

• Some tasks run in parallel to optimize timeline

• Critical path: Planning → Database → Back-End → Front-End → Testing → Documentation

# 11. Milestones

| Major Activity or Milestone | Estimated Milestone Target date | Owner/Reviewer Team Members |
| --- | --- | --- |
| Requirements and Planning Complete | September 30, 2025 | All Team Members |
| UI/UX Design and Wireframes Complete | November 11, 2025 | Talalovic Ababakar |
| Database Implementation Complete | November 18, 2025 | Samin Qureshi |
| Back-End API and Authentication Complete | December 30, 2025 | Samin Qureshi, Soman Ahmad |
| Front-End Mobile App Complete | February 24, 2026 | Pierre-Anthony Eid |
| System Testing and Integration Complete | March 10, 2026 | All Team Members |
| Final Deliverables and Documentation | March 28, 2026 | All Team Members |

# 12. RAM – Responsibility Assignment Matrix

## RACI Model

| Task / Deliverable | Soman Ahmad (Back-End) | Samin Qureshi (Database) | Pierre-Anthony (Front-End) | Talalovic (UI/UX) | Laily Ajellu (Instructor) |
| --- | --- | --- | --- | --- | --- |
| Project Planning & Requirements Analysis | R, A | R | R | R | C, I |
| UI/UX Design & Wireframing | C | C | C | R, A | I |
| Database Design & Implementation | C | R, A | C | I | I |
| Back-End Development (API, Authentication) | R, A | R | C | I | I |
| Front-End Development (iOS/Android) | C | C | R, A | R | I |
| Server Configuration & DevOps | R, A | C | I | I | I |
| Integration & System Testing | R, A | R | R | R | C, I |
| Quality Assurance & Bug Fixes | R | R | R | R | C, I |
| User Acceptance Testing | R | R | R, A | R | C |
| Technical Documentation | R, A | R | R | R | C, I |
| User Documentation & Guides | C | C | R | R, A | I |
| Project Reporting & Status Updates | R, A | R | R | R | I |

### RACI Legend:

| R - Responsible | Person(s) who actually complete the task. Does the work to achieve the task. |
| --- | --- |
| A - Accountable | Person ultimately answerable for the correct and thorough completion of the task. Approves work. Only one 'A' per task. |
| C - Consulted | Person(s) whose opinions are sought. Provides input and expertise. Two-way communication. |
| I - Informed | Person(s) who are kept up-to-date on progress and decisions. One-way communication. |

### Notes:

• All team members share QA responsibility across all phases

• Multiple 'R' assignments indicate collaborative work

• Each task has one 'A' (Accountable) who has ultimate ownership

• Instructor is consulted/informed on all major deliverables and decisions

# 13. Approval

The signatures below indicate their approval of the contents of this document.

| Project Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Instructor | Laily Ajellu |  |  |
| Back-End Engineer | Soman Ahmad | Soman Ahmad | Oct 25, 2025 |
| Database Engineer | Samin Qureshi | Samin Qureshi | Oct 25, 2025 |
| Front-End Engineer | Pierre-Anthony Eid | Pierre-Anthony Eid | Oct 25, 2025 |
| UI/UX Designer | Talalovic Ababakar | Talalovic Ababakar | Oct 25, 2025 |