Project Status Report I

Date of Report Issue/Prepared: February 8, 2025

Report Prepared By Team Members: Samin Qureshi, Soman Ahmad, Pierre-Anthony Eid, Talalovic Akakabar

Employer/Organization (if applicable) : LMNL.app

| Project Name: Project Team: Period Reporting: Overall Project Health | LMNL.app |  |
| --- | --- | --- |
|  | Team 2 |  |
|  | Start Date: Jan 06, 2025 | End Date: Jan 31, 2025 |
|  | Yellow (Warning) |  |

Summary

Project Status Summary

- The initial Minimum Viable Product application has been completed, with all core features fully functional across both iOS and Android platforms - The iOS build is stable and performing as expected, serving as the primary testing and demonstration platform - The Android build is still in progress, with several platform-specific UX bugs that do not appear on the iOS version currently being addressed - The Supabase database is fully operational with Row Level Security enabled, providing secure data access and storage at the row level based on user roles and permissions - The official LMNL.app domain has been purchased for the organization to support branding and future web presence - Development of the Landing Page website remains a priority and is scheduled for the upcoming sprint period - Apple Developer and Google Developer accounts have been set up to facilitate app store submissions and distribution - The user interface has been implemented according to the original design specifications, and a comprehensive colour overhaul has been carried out to establish a premium, health-focused brand identity distinct from competitors - The team is strategically prioritizing core features and evaluating overall scope to ensure quality delivery within the available timeline - The application has been submitted to Apple TestFlight for external beta testing, with the review process currently underway - The back-end architecture utilizes Expo combined with React Native, enabling a single unified codebase that targets both iOS and Android platforms - User authentication has been offloaded to Supabase Auth, providing a production-ready and secure login system without the need to build custom authentication from scratch - The logo has been transitioned from the original four-circle design to a clean text-based wordmark, alongside a full dark-mode colour palette to reinforce the premium brand direction - The front-end features a bottom tab navigation system with five main screens: Home, Search, Create, Alerts, and Profile, each supporting mindful usage tracking

| Accomplishments As Planned | Planned but not Accomplished |
| --- | --- |
| GitHub repository and organization have been established for version control and team collaboration | Resolving remaining iOS and Android bugs, particularly platform-specific UI inconsistencies |
| Initial Minimum Viable Product application completed with all core features functional | Landing Page website development has not yet commenced due to timeline constraints |
| Supabase database has been created with PostgreSQL, real-time subscriptions, and storage buckets | Publishing to App Store and Google Play Store is still pending approval processes |
| Full database schema has been designed and implemented, including tables for profiles, posts, interactions, notifications, push tokens, follows, sponsored posts, and viewed posts | App onboarding experience still requires refinement and user flow optimization |
| Initial technical documentation completed, including Setup.md and README.md for developer onboarding |  |
| Tested application functionality across iOS and Android devices, with working binaries built for both platforms |  |

Upcoming Objectives for Feb 01, 2025 to Mar 7, 2025

- Complete and launch the Landing Page website for LMNL.app to support public-facing branding and user acquisition

- Identify and resolve Android-specific UX bugs that do not appear on the iOS build, ensuring cross-platform consistency

- Submit and publish the application to both the Apple App Store and Google Play Store for public distribution

- Refine and polish the user interface in preparation for the System Implementation 1 deadline, incorporating the new premium dark-mode theme

- Improve and streamline the app onboarding experience by simplifying user flows and conducting internal usability testing

|  |  | Planned Activities/Tasks for Next Period |  |  |
| --- | --- | --- | --- | --- |
| Activity/Task | Assigned To <name/s> |  | Duration <days> | Date |
| Landing Page Website Development | Pierre, Talalovic |  | 10 days | Feb 11 |
| Identify and resolve Android-specific UX bugs not present on iOS | Everyone |  | Entire duration | Mar 7 |

|  | Milestones for Next Period |  |  |
| --- | --- | --- | --- |
| Milestone (Objective) |  | Assigned To | Delivery Date |
| Submit and publish to App Store and Google Play |  | Samin | Mar 7 |
| Identify and resolve Android-specific UX bugs not present on iOS |  | Everyone | Mar 7 |

Managing Issues and Risk (for current reporting period and next period)

| Issues/Problems | Resolution Strategy | Due Date |
| --- | --- | --- |
| Android-specific UX bugs require resolution to achieve cross-platform parity with the stable iOS build | Investigate Android-specific Expo React Native code paths and implement platform safeguards where necessary to ensure consistent behaviour | Mar 7 |
| Landing Page website development has been delayed beyond the original schedule | Allocate dedicated development time for Pierre and Talalovic; leverage an existing template to accelerate the build and reduce time to launch | Feb 11 |
| The app onboarding experience needs refinement to improve first-time user retention | Review and simplify the user onboarding flow; conduct usability testing with team members to identify friction points and improve the first-time experience | Mar 7 |

| Upcoming Risks | Risk Ranking (Hi, Med, Low) | Risk Impact (Hi, Med, Low) | Mitigation Strategy |
| --- | --- | --- | --- |
| The compressed development timeline may not allow completion of all originally planned features | High | High | Prioritize core MVP features and defer non-essential functionality; concentrate development efforts on meeting the System Implementation 1 deadline with a polished, stable product |
| Potential delays in App Store and Google Play review and approval processes | Med | High | Submit builds early to account for review timelines; ensure strict compliance with all app store guidelines; maintain a contingency plan using TestFlight and internal distribution channels for demonstration purposes |
| Team resource availability and cross-functional coordination challenges | Med | Med | Conduct regular team meetings to track sprint progress; maintain clear task assignments with defined ownership; leverage GitHub for code coordination and version control |

NOTE: Attach additional sheets if insufficient space available

Submission Guidelines:

Please submit as “W25_T<team number>_ProjectReport1”.

For e.g., W25_T99_ProjectReport1

This is a group submission i.e. one per group.

Due Dates:

Sunday, Feb 02, 2025 (11:59 p.m.)